Activity 09

# Scheduling

2025-2026

# Objective

Creating, analyzing, and optimizing a project schedule.

# Scenario: Project "Wishlist"

You are the new project manager for a small e-commerce company. Your team is tasked with developing a new "Wishlist" feature for the website. You have three developers, each with a specialty:

- Salah (Backend)

- Ahmed (Frontend)

- Zyed (DB/QA)

Project Brief: Task List (WBS)

Here is the high-level task list your team has compiled.

| Task ID | Task Name | Duration (Days) | Resource(s) | Predecessor(s) |
| --- | --- | --- | --- | --- |
| A | Kickoff Meeting | 1 | Salah, Ahmed | - |
| B | Define Feature Specs | 2 | Salah, Ahmed , Zyed | A |
| C | Build API | 4 | Salah | B |
| D | Implement DB Schema | 3 | Zyed | B |
| E | Design UI Mockups | 3 | Ahmed | B |
| F | Build UI Components | 5 | Ahmed | E |
| G | Write Test Cases | 3 | Zyed | B |
| H | Integrate API & DB | 2 | Salah, Zyed | C, D |
| I | Final Integration & System Test | 3 | Ahmed, Zyed | F, G, H |
| J | Deploy to Production | 1 | Salah | I |

# Activity Steps

## Initial Network Diagram & Critical Path

First, let's map out the project as-is.

- Draw the Diagram: Using an online whiteboard, create an network diagram based on the task list. For nodes use a six-compartment box.

- Calculate Schedule: Perform a Forward Pass and Backward Pass to determine the Early Start (ES), Early Finish (EF), Late Start (LS), and Late Finish (LF) for every task.

- Find the Critical Path:

  - What is the total project duration?

  - Identify the critical path (or paths) by finding the sequence of tasks with zero slack (Slack = LS - ES).

## What-If Analysis - Leads & Lags

Modify your diagram from Part 1 to reflect these new scenarios.

- Scenario 1 (Lag): The team decides that Task G (Write Test Cases) can only begin after the UI mockups are finished and approved. This adds a 1-day lag after Task E. The new dependency for G is E (FS+1d).

- Scenario 2 (Lead/Fast-Tracking): To speed things up, Task F (Build UI Components) can start when Task E (Design UI Mockups) is 2/3 complete. Task E takes 3 days, so Task F can start 1 day before E finishes. This is a Finish-to-Start with a 1-day lead (FS-1d).

Task: Re-calculate the ES, EF, LS, LF, and the critical path with these new dependencies.

- Has the total project duration changed?

- Has the critical path changed?

## Resource Visualization

- Create Gantt chart: Draw a Gantt-style chart, but create three horizontal "swimlanes," one for each team member: Salah, Ahmed , and Zyed. (Tasks with multiple resources should be duplicated: Task T becomes Task Ta and Tb with a start to start constraint).

- Plot the Schedule: Using your (updated) schedule from Part 2, draw each task as a bar on its Earliest Start (ES) date in the correct resource's swimlane.

- Identify Conflicts: Examine your swimlane chart. Do you see any days where a single resource (e.g., Zyed) is assigned to two or more tasks simultaneously?

## Resource Leveling

- Analyze the Conflict:

  - Which resource is over-allocated?

  - Which tasks are in conflict?

  - Look at the slack for the conflicting tasks.

- Propose a Solution: Apply resource leveling. The easiest way is to delay the start of one of the conflicting tasks until the other is finished.

  - Which task should you delay? Hint: Always try to delay the task with the most slack first, as it's less likely to affect the critical path.

- Create a New Schedule: Implement your solution by adding a new precedence (e.g., Task D must finish before Task G can start).

- Re-compute: Recalculate the ES, EF, LS, LF, and slack for all tasks based on this new, leveled schedule.

## Final Analysis & Report

Conclude the activity by analyzing the results of your leveling.

- Final Critical Path: What is the new critical path and the new final project duration?

- Impact: Did leveling the resources extend the project? Why or why not?

- What If...: What if your leveling did extend the project, but management insists on the original deadline? Based on your lecture, name one schedule compression technique (like crashing or fast-tracking) you could apply to the new critical path to shorten it.

# Submission

Be sure to include all group members' names in your submission.