## Risk Register
Expanded Risk Register
| Risk name | Risk Description | Risk Mitigation | Probability | Impact | Risk Exposure | First Indicator | Mitigation/Management Stategies
| Agile 1 |  |  | Agile 1
1 | Scope Creep | One of the many tasks for a product owner is managing and prioritizing the backlog, if they fail to do that, we can see that the scope creeping issu begins to happen. This is partially due to scrums openness to change continuously. | During planning, must integrate a sprint goal. This is so that we can still have changes that happen throughout the project, maintaing scrums values, but they must align with that sprints goal. We can move it to the product backlog if it doesn't excactly work with the sprint goal. | 3 | 4 | 12 | Sudden features skill-matching features or even user stories being added in the middle of a sprint without any commitment adjustment nor checking alignment with that sprints goal. | Abiding by our sprint goal, even if stakeholders suggest something new mid sprint, we can keep that in the product backlog.
2 | Lack of awareness of Scrum method | As one of the disadvatnages of scrum, not being aware of it's principles can actually defeat its purpose. If members aren't used to the quick-paced meeting and adapting to continous changes this could risk the projects success. | Before an organization shifts to scrum methodology, they need to preapre all members involved by having introductory training sessions. This can prepare those who don't know to understand the way the method works. | 3 | 3 | 9 | Members missing dailystand-ups and just not engaging with the team. Lacking the skills to communicate effectively and plan are early indicators. | Ensuring all organization staff is entirely aware of sprint methods, and holding them accountable in some way according to our policy.
3 | Going over the budget and time | Scrum focuses more on short-term goals within the sprint instead of the main big-picture plans. This allows some slip-ups to happen in terms of deadlines and fincancial. | Plan sprints according to realistic standards of the teams abilities. Also, utilizing a sprint burndown chart that we can track daily to ensure we don't miss any red flags. | 4 | 4 | 16 | Mid-sprint, the sprint burndown chart going above the line. As well as being aware of the hisotrical velocity, yet still going against it knowing the staffs skills. | Tracking the sprint burndown chart and planning according to it. We must maintain this as to avoid missing budget or even deadlines
4 | Developer burnout | Since scrum includes fast sprints and constant iterations, it can tire out members who aren't exactly used to it. | An important concept to mitagate this and the previous risk is hisotrical velocity, which is the average story points completeed per sprint. When we know our teams historical velocity, we can make plans that could potentially match reality at a higher chance.We can also move any undone work to a backlog without threatening our team with any penalites. | 3 | 4 | 12 | Completely dismissing any complaints from the team regarding the specific tasks within a sprint. Especially if the sprints velocity is obviously higher than the team is able to do, according to their history. | Sticking to the historical velocity, and portraying the skills of listening to our staff.
| Agile 2 (XP) |  |  | Agile 2
1 | Insufficient Test-Driven Development (TDD) Skills | XP relies on writing automated tests before implementing code. If the team lacks experience with TDD, tests may be poorly designed or the practice may be abandoned, allowing defects in CV parsing, match scoring, or portal workflows to remain undetected. | Provide a short TDD workshop and agree on test-writing standards before applying the practice to Phase 1 features. | 3 | 4 | 12 | Developers frequently skip writing tests first, or automated tests fail to cover important matching and portal behavior. | Pair less-experienced developers with experienced team members; review test coverage during code reviews; include test quality in the Definition of Done.
2 | Pair-Programming Scheduling Conflicts | XP encourages developers to work in pairs. In Fursah's matrix structure, team members may have competing responsibilities assigned by functional managers, making it difficult to maintain pairing sessions and slowing implementation. | Agree on protected pairing time and coordinate developer availability with functional managers before each development cycle. | 4 | 3 | 12 | Pairing sessions are repeatedly cancelled, or tasks remain blocked while waiting for an available partner. | Plan pairing rotations; use shared calendars; document decisions and code context; review whether pairing is being applied to the highest-risk or most complex tasks.
3 | Continuous-Integration Build Instability | XP emphasizes frequent code integration. If automated builds and tests are unreliable or the team integrates incompatible changes, defects may repeatedly break the shared codebase and delay work across the Smart Matching Engine and both portals. | Configure a shared automated build and test pipeline and require changes to pass the agreed checks before integration. | 3 | 4 | 12 | The main branch frequently fails automated builds or integration defects recur across components. | Keep changes small; fix broken builds promptly; automate unit and integration tests; assign responsibility for monitoring pipeline health and reviewing recurring failures.
4 | Refactoring Introduces Regressions | XP encourages frequent refactoring to keep code maintainable. If the team changes internal code without adequate automated regression tests, previously working CV parsing, matching scores, job recommendations, or application functions may break. | Run automated unit and regression tests before and after refactoring, and refactor in small, reviewable changes. | 3 | 4 | 12 | Previously passing tests fail after code restructuring, or defects repeatedly appear in features that were already completed. | Maintain regression tests for critical workflows; require peer review for high-impact changes; use version control and revert unsafe changes promptly.
| Plan-Driven 1 |  |  | Plan-Driven 1
1 | Fixed requirements may no longer meet project needs | Requirements are approved at the start of the project and stay unchanged throughout the development. Once the platform is fully launched job market needs and HRSD policies may have changed which results in features that are no longer up to date. | Review project requirements with HRSD at each approval stage and follow a process to approve the necessary changes. | 4 | 4 | 16 | HRSD introduces new labor policies or vision 2030 goals or Stakeholders might request changes after the project requirements have been approved. | Apply formal change control board involving HRSD and functional managers, keep a list of prioritized lists of changes that will be implemented after the platform launches, include extra time in the project schedule to handle approved changes.
2 | User rejection during acceptance testing | Job seekers, employers, and HRSD would only be able to test the platform at the final stages. They may be unsatisfied with issues such as usability, language, support, or how the system works, which could be costly and time-consuming to fix at the final stages. | Create UI interface prototypes during the design phase and ask users to test and approve them before the final design is approved. | 3 | 5 | 15 | Users could give negative feedback on the prototypes or stakeholders could often not attend design review meetings. | Requires stakeholders to review and approve the UI interface designs, involve employers, jobseekers, and people with disabilities in design evaluations, allocate extra money to fix issues during the final testing.
3 | Matching engine fails final testing | The NLP matching engine should be fully planned before development starts, and is only tested at the final stage. If the matching accuracy is too low, there may not be enough money or time to improve the design. | Test the NLP approach using sample resumes, and job listings during the requirements stage to ensure they are suitable before finalizing the design. | 3 | 5 | 15 | Initial test show the system would not match jobs accurately or could have trouble understanding information in Arabic resumes. | Set a minimum accuracy level for job matching accuracy the system must achieve, have a back up plan that matches jobs using keywords, assignment NLP experts from the matrix organization at the earliest stages of the project.
4 | Failure during full system launch | Waterfall delivers the entire system components in one go, including the matching engine, portals, networking, and government integrations all at the very same time. If one component has a problem or a government system fails to connect it could delay or effect the whole national launch. | Test the complete platform with a selected group of users and government agencies before the national launch | 3 | 5 | 15 | Testing shows issues in several parts of the system or connections with government agencies are delayed. | Create a detailed integration testing plan with entry and exit criteria, prepare a backup and recovery plan in case problems occur during the launch, make sure government agency systems are ready to connect at each approval stage.
| Plan-Driven 2 |  |  | Plan-Driven 2
1 | Late Requirement Changes | Changes in employer recruitment requirements or government integration specifications after requirements approval may require extensive rework of completed phases. | Validate requirements with employers and government stakeholders before final approval. | 4 | 4 | 16 | New requirements requested after requirements sign-off. | Apply formal change control, assess the impact on scope and schedule, and update approved documentation.
2 | Late Discovery of Matching Errors | Problems with the NLP-based matching engine may only become apparent during system testing, requiring changes to earlier design and implementation work. | Define measurable matching accuracy criteria and review the matching design before implementation. | 3 | 5 | 15 | Matching results fail acceptance criteria during system testing. | Review NLP matching requirements early, establish measurable acceptance criteria, and allocate time for corrective testing.
3 | Delayed Stakeholder Validation | Job seekers and employers may not evaluate the working platform until late in development, allowing usability problems to remain undiscovered. | Conduct formal stakeholder reviews of requirements and interface designs before development. | 4 | 4 | 16 | Major usability issues identified during stakeholder acceptance testing. | Conduct stakeholder reviews at requirements and design milestones and document feedback before implementation.
4 | Sequential Phase Dependencies | Delays in completing the platform architecture or government integration specifications may prevent subsequent development and testing activities from starting on schedule. | Establish phase milestones and monitor critical dependencies throughout development. | 3 | 4 | 12 | A development phase misses its milestone and delays dependent activities. | Track phase dependencies, monitor critical milestones, and allocate schedule contingency for delays.
Risk Exposure = Probability × Impact.